## Sheet1
Asset | About | Priority | Started | Finished
Twilight Flash rig | Head needs finishing, horn, neck and wings all need to be vectored too | High | 2015-03-07
AJ standings | Idle frame done… Though might need to be redone | High | 2015-03-07
GUI | Just lost an hours worth of work on it 'cause of human error. Putting it off for a bit | Medium | 2015-03-07
New GUI concept |  | Low | 2015-03-09
Pinkie's Cannon | DONE! | Done | 2015-03-08 | 2015-03-09
Twilight's Stage | Finished a pillar, need to finish the chairs an' stuff. May change the floor layout a bit, added tree trunks to the pillars. | High | 2015-03-09
AJ Forward Walk | Handed over to CK. | High | 2015-03-16
RD's Cloud | Mostly done, just fine-tuning most of the kinks out | medium | 2015-03-25
RD Keyframes | Took keyframes of RD's moves from the streams. | High | 2015-03-27