## Sheet1
2015-03-16
Asset/Task Name | Asset/Task Type | Description | Developer(s) | Priority | Status | Notes | Feedback
AJ_standings | Animation | Key poses of Applejack's Light/Med/Heavy Attacks. | Blurred | High | Sketch Phase
TS_rig | Flash Rig | Twilight Sparkle Flash puppet, used for animations. | Caleb | High | Vectoring Phase | Must Fix up the neck and eyes, Adding extra eyelashes.
MF_site_updat | Web-Design | Update the theme of the website. | Daniel, Caleb | Medium | Programming Phase
AJ_crouchings | Animation | Animate Applejack's crouched moves. | Caleb | High | Sketch Phase
GUI | PSD | In-Game fight UI | Caleb, DSC, Kiwi | High | Concept Phase? | I have to finsh the scan lines and polish,
AJ_standings | Animation | Applejack's Standing Idle. | Shizam, Caleb | High | Keyframing
AJ_splash_art | Artwork | Applejack's Splash art | Kiwi, Caleb | Medium | Flash Sprited
maneframedev | Website | Site programming new theme | Daniel | Low | N/A
Twilight's_castle | Stage | Flash stage vector. | Caleb | High | Vectoring Phase
AJ_strut_forward | Animation | Applejack's forward walk animation | Caleb | High | Clean Up | Damn legs
Charstates | Unreal Engine | Enumerators for AJ's states | Caleb | High | Still listing